## Sheet1
ISSUE ID: | DATE IDENTIFIED: | FEATURE: | DESCRIPTION: | EXPECTED RESULT: | ACTUAL RESULT: | PRIORITY: | DEBUGGING METHOD: | CAUSE: | FIX APPLIED: | RETEST RESULT: | STATUS:
ISS-001 | 2026-08-05 | SQLite Database | SQLiteException thrown on initial database connection attempt. | Database creates tables smoothly without crashing. | Exception thrown regarding local file access path. | High | VS Exception Breakpoint / Output Window | FileSystem.AppDataDirectory path string was uninitialized prior to connection. | Used Path.Combine(FileSystem.AppDataDirectory, "volunteerconnect.db3") in DatabaseService.cs. | Database file created cleanly on emulator. | Resolved
ISS-002 | 2026-08-05 | SQLite Seed Data | Sample volunteer opportunities duplicated every time app reopens. | Seed data inserts only once when the app is first used. | Opportunity table duplicated rows on relaunch (10, 15, 20...). | High | VS Breakpoint / Local SQLite Inspection | Missing table count check before running InsertAllAsync(). | Added if (await _db.Table<VolunteerOpportunity>().CountAsync() == 0) check in DatabaseService.cs. | Verified exactly 5 unique records remain across 3 app relaunches. | Resolved
ISS-003 | 2026-08-05 | Privacy Validator | Contact validation passed empty string containing spaces (" "). | Block whitespace-only contact entries. | Whitespace passed regex validation successfully. | Medium | Variable Inspection / Unit Testing | Missing string.IsNullOrWhiteSpace() check prior to regex execution. | Added Trim() and IsNullOrWhiteSpace() pre-validation in PrivacyValidator.cs. | Whitespace inputs correctly blocked. | Resolved
ISS-004 | 2026-08-05 |  | Navigation route missing error when tapping opportunity card. |  |  |  | Registered routes in AppShell.xaml.cs using Routing.RegisterRoute |  |  |  | Resolved
ISS-005 | 2026-08-05 | MAUI Compilation | Build failed with missing type errors for OpportunityDetailsPage, RegistrationPage, MyRegistrationsPage, EditRegistrationPage, and PrivacyPage. | App compiles cleanly after adding page references to MauiProgram.cs and AppShell.cs. | Compiler threw CS0246 errors for missing classes in VolunteerConnect.Views. | High | Visual Studio Error List Window | AppShell.xaml.cs and MauiProgram.cs declared routing and DI registrations before the XAML ContentPages were added to the project. | Created all 5 remaining ContentPage XAML and C# code-behind files in Views/ folder. | Project compiles with 0 errors. | Resolved
ISS-006 | 2026-08-05 | Services / Regex | Compiler error on Regex.IsMatch() inside PrivacyValidator.cs. | Contact detail validation checks string format without compiler error. | Compiler threw error CS0029 regarding non-static/instance invocation of Regex.IsMatch. | Medium | Visual Studio Compiler / Error List | Incorrect overload syntax used when calling Regex.IsMatch() static method. | Updated PrivacyValidator.cs to pass pattern string directly into static Regex.IsMatch(input, pattern, options). | Valid email and phone inputs return true; invalid inputs return false. | Resolved
SS-007 | 2026-08-05 | XAML Parsing | OpportunityDetailsPage.xaml threw unexpected XML declaration parser error and missing control name errors. | XAML parses cleanly and binds named labels (TitleLabel, DateLabel, etc.) to code-behind. | Build failed on line 17 due to duplicate root tag; C# code-behind lost reference to controls. | High | VS Error List / Output Window | Duplicate <?xml ...?> declaration and <ContentPage> root tag accidentally pasted into OpportunityDetailsPage.xaml. | Removed duplicate XML root block; executed Clean & Rebuild. | Build succeeded with 0 errors; controls properly bound. | Resolved
ISS-008 | 2026-08-05 | MAUI Build / Compiler | CS0229 ambiguous reference errors between OpportunityDetailsPage.InitializeComponent() and controls (TitleLabel, DateLabel, etc.). | Clean compilation with a single auto-generated partial class for OpportunityDetailsPage. | Compiler threw multiple CS0229 duplicate symbol errors during build. | High | VS Error List / File Explorer Audit | Stale auto-generated .g.cs files remained in local obj directory after resolving XAML syntax error, causing duplicate symbol declarations. | Closed Visual Studio, purged local bin and obj build directories, reopened solution, and executed full Rebuild. | Build succeeded with 0 errors; ambiguous symbol warnings cleared. | Resolved
ISS-009 | 2026-08-05 | Visual Studio IDE | "There were build errors" execution dialog prompt appeared when hitting F5. | App builds with zero errors and launches updated assembly on emulator. | IDE prompted to run last successful build due to unhandled compiler errors in active build configuration. | High | VS Error List Audit / Output Window | Solution attempted deployment while stashed build artifacts or missing view registrations remained unresolved in active configuration. | Cancelled execution, reviewed Error List, closed open XAML tabs, and performed full Rebuild Solution. | Project built cleanly with zero errors; application launched on target emulator. | Resolved
ISS-010 | 2026-08-05 | MSBuild / MAUI Imports | MSBuild file lock errors on Windows MsixContent DLLs and missing namespace errors for QueryProperty / ContentPage. | Clean build and deployment to emulator without process lock exceptions. | Build failed with file access lock exceptions in obj\Debug\ and CS0246 missing namespace errors in OpportunityDetailsPage.xaml.cs. | High | Task Manager Audit / VS Error List | Background MSBuild.exe processes locked intermediate obj output files; missing Microsoft.Maui.Controls namespace import in code-behind. | Terminated MSBuild tasks, deleted bin and obj directories, added using Microsoft.Maui.Controls; to OpportunityDetailsPage.xaml.cs, and executed Rebuild. | Solution built cleanly with 0 errors; app deployed successfully. | Resolved
ISS-011 | 2026-08-05 | MAUI Compilation | CS0229 ambiguous symbol errors between OpportunityDetailsPage.InitializeComponent() and control fields after Solution Clean. | Solution compiles with single auto-generated partial class file for OpportunityDetailsPage. | Compiler generated duplicate symbol definitions in intermediate build files prior to Rebuild execution. | High | VS Error List / File Explorer Audit | Intermediate build artifacts lingering during active Clean/Rebuild cycle before full compiler cache refresh. | Executed full Rebuild Solution to regenerate unified .g.cs partial classes across all 7 Views. | Project compiled cleanly with 0 errors; application running on target emulator. | Resolved